## Input
Start Chainage | Finish Chainage | Section Size | No of columns | Area of work | Section Name | Section Define | From Chainage | To Chainage
62000 | 47000 | 1000 |  | 15 | 1st Section Name | Section 1 | 62000 | 61000
[5 empty] | 2nd Section Name | Section 2 | 61000 | 60000
[5 empty] | 3rd Section Name | Section 3 | 60000 | 59000
[5 empty] | 4th Section Name | Section 4 | 59000 | 58000
[5 empty] | 5th Section Name | Section 5 | 58000 | 57000
[5 empty] | 6th Section Name | Section 6 | 57000 | 56000
[5 empty] | 7th Section Name | Section 7 | 56000 | 55000
[5 empty] | 8th Section Name | Section 8 | 55000 | 54000
[5 empty] | 9th Section Name | Section 9 | 54000 | 53000
[5 empty] | 10th Section Name | Section 10 | 53000 | 52000
[5 empty] | 11th Section Name | Section 11 | 52000 | 51000
[5 empty] | 12th Section Name | Section 12 | 51000 | 50000
[5 empty] | 13th Section Name | Section 13 | 50000 | 49000
[5 empty] | 14th Section Name | Section 14 | 49000 | 48000
[5 empty] | 15th Section Name | Section 15 | 48000 | 47000

## 3WLA
St Date | End Date | Task ID | Task Description | 3WLA Task Description | Resources | Quantity | Responsible Manager | Location | Chainage From | Chainage To
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 1 | 100 | Chris Nolan | A Track | 54000 | 54800
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 1 |  | Chris Nolan | A Track | 54800 | 55000
2019-03-29 | 2019-03-29 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 52800 | 53000
2019-04-01 | 2019-04-01 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 53600 | 54000
2019-03-30 | 2019-03-30 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54000 | 54400
2019-03-30 | 2019-03-30 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54400 | 54800
2019-04-19 | 2019-04-19 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 1st Rock Saw Cut | A J Willcock Gang 2 |  | Chris Nolan | A Track | 54800 | 55000
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Chris Nolan | A Track | 53000 | 53100
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53100 | 53200
2019-04-08 | 2019-04-08 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53200 | 53400
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53200 | 53300
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 53800 | 54000
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 54100 | 54200
2019-04-09 | 2019-04-09 | A0001 | A J Wilcox Rock Saw Cut- Section 2B1 52850 - 54750 (1900m) | 2nd Rock Saw Cut | A J Willcock Gang 1 |  | Simon Powell | B Track | 54200 | 54300
2019-04-12 | 2019-04-12 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-13 | 2019-04-13 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-15 | 2019-04-15 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-16 | 2019-04-16 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-17 | 2019-04-17 | A0002 | Vaccum excavation of exclusion zones - Section 2B1 52850 - 54750 (1900m) | Vac Ex - Trial holes Extensions | BBV Gang 1 |  | Richard H | Central Reservation | 52800 | 53000
2019-04-15 | 2019-04-15 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 8 No | Richard H | Central Reservation | 54000 | 55000
2019-04-16 | 2019-04-16 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 6 No | Richard H | Central Reservation | 54000 | 55000
2019-04-17 | 2019-04-17 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 4 No | Richard H | Central Reservation | 54000 | 55000
2019-04-18 | 2019-04-18 | A003 | Hand dig of exclusion zones - Section 2B1 52850 - 54750 (1900m) (Approx 8 No) | Hand dig of exclusion zones | Gangs NSWRA | 2 No | Richard H | Central Reservation | 54000 | 55000

## Sheet1
|  | Chainage --> | 62000 | 61900 | 61800 | 61700 | 61600 | 61500 | 61400 | 61300 | 61200 | 61100 | 61000 | 60900 | 60800 | 60700 | 60600 | 60500 | 60400 | 60300 | 60200 | 60100 | 60000 | 59900 | 59800 | 59700 | 59600 | 59500 | 59400 | 59300 | 59200 | 59100 | 59000 | 58900 | 58800 | 58700 | 58600 | 58500 | 58400 | 58300 | 58200 | 58100 | 58000 | 57900 | 57800 | 57700 | 57600 | 57500 | 57400 | 57300 | 57200 | 57100 | 57000 | 56900 | 56800 | 56700 | 56600 | 56500 | 56400 | 56300 | 56200 | 56100 | 56000 | 55900 | 55800 | 55700 | 55600 | 55500 | 55400 | 55300 | 55200 | 55100 | 55000 | 54900 | 54800 | 54700 | 54600 | 54500 | 54400 | 54300 | 54200 | 54100 | 54000 | 53900 | 53800 | 53700 | 53600 | 53500 | 53400 | 53300 | 53200 | 53100 | 53000 | 52900 | 52800 | 52700 | 52600 | 52500 | 52400 | 52300 | 52200 | 52100 | 52000 | 51900 | 51800 | 51700 | 51600 | 51500 | 51400 | 51300 | 51200 | 51100 | 51000 | 50900 | 50800 | 50700 | 50600 | 50500 | 50400 | 50300 | 50200 | 50100 | 50000 | 49900 | 49800 | 49700 | 49600 | 49500 | 49400 | 49300 | 49200 | 49100 | 49000 | 48900 | 48800 | 48700 | 48600 | 48500 | 48400 | 48300 | 48200 | 48100 | 48000 | 47900 | 47800 | 47700 | 47600 | 47500 | 47400 | 47300 | 47200 | 47100 | 47000
|  | Section --> | Section 1 | [9 empty] | Section 2 | [9 empty] | Section 3 | [9 empty] | Section 4 | [9 empty] | Section 5 | [9 empty] | Section 6 | [9 empty] | Section 7 | [9 empty] | Section 8 | [9 empty] | Section 9 | [9 empty] | Section 10 | [9 empty] | Section 11 | [9 empty] | Section 12 | [9 empty] | Section 13 | [9 empty] | Section 14 | [9 empty] | Section 15
Date | Task ID | Task
2019-08-05 | A0001 | Activity 1 | Gang 1
Gang 2
Gang 3
Gang 4
2019-08-06 | A0001 | Activity 1 | [5 empty] | Gang 5
| A0002 | Activity 2 | [11 empty] | Gang 2
2019-08-07 | A0003 | Activity 3 | [21 empty] | Gang 1
2019-08-09 | A0004 | Activity 4 | [31 empty] | Gang 2
2019-08-12 | A0005 | Activity 5 | [41 empty] | Gang 3
2019-08-13 | A0006 | Activity 6 | [51 empty] | Gang 4
2019-08-14 | A0007 | Activity 7 | [61 empty] | Gang 5
2019-08-15 | A0008 | Activity 8 | [71 empty] | Gang 1
2019-08-16 | A0009 | Activity 9 | [81 empty] | Gang 1
2019-08-19 | A0010 | Activity 10 | [91 empty] | Gang 3
2019-08-20 | A0011 | Activity 11 | [101 empty] | Gang 4
2019-08-21 | A0012 | Activity 12 | [111 empty] | Gang 5
2019-08-22 | A0013 | Activity 13 | [121 empty] | Gang 2
Gang 4
2019-08-23 | A0014 | Activity 14 | [131 empty] | Gang 1
Gang 2
Gang 3
2019-08-24 | A0015 | Activity 15 | [141 empty] | Gang 1
Gang 5

## Sheet1 (2)
|  | Chainage --> | 62000 | 61900 | 61800 | 61700 | 61600 | 61500 | 61400 | 61300 | 61200 | 61100 | 61000 | 60900 | 60800 | 60700 | 60600 | 60500 | 60400 | 60300 | 60200 | 60100 | 60000 | 59900 | 59800 | 59700 | 59600 | 59500 | 59400 | 59300 | 59200 | 59100 | 59000 | 58900 | 58800 | 58700 | 58600 | 58500 | 58400 | 58300 | 58200 | 58100 | 58000 | 57900 | 57800 | 57700 | 57600 | 57500 | 57400 | 57300 | 57200 | 57100 | 57000 | 56900 | 56800 | 56700 | 56600 | 56500 | 56400 | 56300 | 56200 | 56100 | 56000 | 55900 | 55800 | 55700 | 55600 | 55500 | 55400 | 55300 | 55200 | 55100 | 55000 | 54900 | 54800 | 54700 | 54600 | 54500 | 54400 | 54300 | 54200 | 54100 | 54000 | 53900 | 53800 | 53700 | 53600 | 53500 | 53400 | 53300 | 53200 | 53100 | 53000 | 52900 | 52800 | 52700 | 52600 | 52500 | 52400 | 52300 | 52200 | 52100 | 52000 | 51900 | 51800 | 51700 | 51600 | 51500 | 51400 | 51300 | 51200 | 51100 | 51000 | 50900 | 50800 | 50700 | 50600 | 50500 | 50400 | 50300 | 50200 | 50100 | 50000 | 49900 | 49800 | 49700 | 49600 | 49500 | 49400 | 49300 | 49200 | 49100 | 49000 | 48900 | 48800 | 48700 | 48600 | 48500 | 48400 | 48300 | 48200 | 48100 | 48000 | 47900 | 47800 | 47700 | 47600 | 47500 | 47400 | 47300 | 47200 | 47100 | 47000
|  | Section --> | Section 1 | [9 empty] | Section 2 | [9 empty] | Section 3 | [9 empty] | Section 4 | [9 empty] | Section 5 | [9 empty] | Section 6 | [9 empty] | Section 7 | [9 empty] | Section 8 | [9 empty] | Section 9 | [9 empty] | Section 10 | [9 empty] | Section 11 | [9 empty] | Section 12 | [9 empty] | Section 13 | [9 empty] | Section 14 | [9 empty] | Section 15
Date | Task ID | Task
2019-08-05 | A0001 | Activity 1 | Gang 1
Gang 2
Gang 3
Gang 4
| A0050 | Activity 50 | [23 empty] | Gang 1
2019-08-06 | A0001 | Activity 1 | [5 empty] | Gang 5
| A0002 | Activity 2 | [11 empty] | Gang 2
2019-08-07 | A0003 | Activity 3 | [21 empty] | Gang 1
2019-08-09 | A0004 | Activity 4 | [31 empty] | Gang 2
2019-08-12 | A0005 | Activity 5 | [41 empty] | Gang 3
2019-08-13 | A0006 | Activity 6 | [51 empty] | Gang 4
2019-08-14 | A0007 | Activity 7 | [61 empty] | Gang 5
2019-08-15 | A0008 | Activity 8 | [71 empty] | Gang 1
2019-08-16 | A0009 | Activity 9 | [81 empty] | Gang 1
2019-08-19 | A0010 | Activity 10 | [91 empty] | Gang 3
2019-08-20 | A0011 | Activity 11 | [101 empty] | Gang 4
2019-08-21 | A0012 | Activity 12 | [111 empty] | Gang 5
2019-08-22 | A0013 | Activity 13 | [121 empty] | Gang 2
Gang 4
2019-08-23 | A0014 | Activity 14 | [131 empty] | Gang 1
Gang 2
Gang 3
2019-08-24 | A0015 | Activity 15 | [141 empty] | Gang 1
Gang 5